## Combined Milestones List
# | Milestone Type | Milestone | Milestone Narrative | Responsibility | Due Date | Date Calculation | Status | Comments as of 3/11/21
1 | Both | Industry Meeting | NANPA hosts meeting with all carriers operating in the 82 NPAs to reach consensus on a single set of implementation dates for 10-digit dialing (10DD) and appropriate milestone dates. NANPA to have a proposal prepared to share with the industry at this meeting. | NANPA and affected carriers | 2020-08-14 | No later than 8/16/2020 | COMPLETE | Notice of meeting record sent. NANPA sent notice of posting Planning Letter to https://nationalnanpa.com/pdf/PL_544.pdf on 08/18/20, Notice of meeting record sent 08/25/20. Planning Letter 556 supersedes PL-544 and posted to NANPA website on January 8, 2021. https://nationalnanpa.com/planning_letters/planning_letters_2021.html
2 | Customer Education | Deadline to develop verbiage for first customer notice | Develop and supply template for first customer notification, a simple message about the permissive dialing "effective date" so customers can start practicing dialing 10 digits and reprogramming CPE. Message must outline what customers need to do to prep for mandatory 10DD. Carriers can then tweak as needed depending on whether they want to send the same message to all customers, tweak for business customers, tweak for customers in particular NPAs, etc. | NANPA | 2020-11-25 | 5 months (150 days) prior to permissive effective date | COMPLETE | Addressed potential customer letters for permissive and mandatory dialing during 10/1/20 meeting. Notice of meeting record sent 10/20/20.
3 | Customer Education | Deadline to develop and send first round of special letters | Develop and send first round of "special letters" to Directory Publishers, Coin Operated Payphone Providers, Alarm Associations, Highway Call Box Operators, and 911 State/County Coordinators & PSAPs advising of the permissive dialing effective date and the mandatory dialing effective date, and what each of these types of groups need to do to prep for mandatory 10DD. Supply these templates to industry as well in case carriers want to use them to supplement their own customer notifications. | NANPA | 2020-12-25 | 4 months (120 days) prior to permissive effective date | COMPLETE | 1. Sample templates of "Special Letters" discussed during 11/20/20 call. Letters posted to https://nationalnanpa.com/transition_to_10_digit_dialing_for_988/index.html on 11/30/20. 2. All first round "special letters" were sent to State Regulators, Directory Publishers, Coin Operated Payphone Providers, Alarm Associations, Highway Call Box Operators, Telecom Associations, Elevator Associations and Regulatory Agencies, Tribal Agency Offices, TTY Providers and 911 State/County Coordinators & PSAPs by 12/25/20.
4 | Customer Education | Deadline to send first notice to PSAPs, PSALI and County Coordinators | Develop and send first notice to PSAPs, PSALI and County Coordinators of upcoming permissive and mandatory 10-digit dialing effective dates and advise that they need to update any speed calling or call forwarding numbers to 10 digits after the permissive 10-digit dialing effective date | 911 Providers | 2020-12-25 | 4 months (120 days) prior to permissive effective date | COMPLETE | This milestone is considered completed.
5 | Customer Education | Deadline to develop verbiage for first press release | Develop and supply verbiage for a press release to announce the permissive and mandatory 10-digit dialing effective dates. Provide verbiage to industry, FCC so they can issue press releases as well, as needed. | NANPA | 2021-02-23 | 2 months (60 days) prior to permissive effective date | COMPLETE | Press release agreed upon at the industry meeting on February 11, 2021. The press release has been posted to the NANPA website at https://nationalnanpa.com/transition_to_10_digit_dialing_for_988/index.html
6 | Customer Education | Deadline for carriers to educate employees internally | Carriers to distribute information and update internal websites about the 82 NPAs to transition to 10-digit dialing internally as job aid for customer-facing employees to answer customer questions. There should not be a need for customer-facing employees to refer customer questions to the NANPA, the FCC or the state commissions. | Carriers | 2021-02-23 | 2 months (60 days) prior to permissive effective date | COMPLETE
7 | Customer Education | Deadline to re-send first round of special letters as a reminder | Send second round of "special letters" again to Directory Publishers, Coin Operated Payphone Providers, Alarm Associations, Highway Call Box Operators, and 911 State/County Coordinators & PSAPs, reminding them of the permissive dialing effective date and the mandatory dialing effective date, and what each of these types of groups need to do to prep for mandatory 10DD. Supply these templates to industry as well in case carriers want to use them to supplement their own customer notifications. | NANPA | 2021-03-10 | 45 days prior to permissive effective date | COMPLETE | All second round "special letters" were sent to 911 State/County Coordinators & PSAPs, Directory Publishers, Coin Operated Pay Telephone Providers, Alarm Associations, Highway Call Box Operators, Telecom Associations, Elevator Regulatory Agencies, Tribal Agency Offices, Seniors and TTY Providers by 3/10/2021.
8 | Customer Education | Deadline to send first customer notice | Issue first customer notification. Carriers using bill messages may want to have these run multiple months rather than just one month to help ensure customers are aware of the upcoming dialing changes. | Carriers | 2021-03-25 | 30 days prior to permissive effective date | COMPLETE | Carriers must notify NANPA via 988@somos.com when this milestone is completed. Include in email: Provider Name, OCN(s), State(s) and NPA(s).
9 | Customer Education | Deadline to update carrier websites and social media | Update social media and external websites with information about the 82 NPAs that will transition to 10DD, noting the permissive 10DD effective date and the mandatory 10DD effective date so that customers can find relevant information. | Carriers (voluntary) | 2021-03-25 | 30 days prior to permissive effective date | COMPLETE
10 | Technical | Deadline for BIRRDS/LERG updates | All carriers must update their CO codes in BIRRDS/LERG via their AOCN to reflect 10 digits for Terminating Digits at End Office (TD-EO) and 10 digits for Terminating Digits at Access Tandem (TD-AT). | Carriers | 2021-04-10 | 14 days prior to permissive effective date |  | Effective date in BIRRDS should be no later than 9/24/2021
11 | Technical | Provide carrier contact information | Provide carrier contact information to NANPA for troubleshooting of any permissive 10-digit dialing issues | Carriers | 2021-04-10 | 14 days prior to permissive effective date |  | Provide carrier contact information via 988@somos.com. Include in email: State(s), Provider Name, Primary Contact, Telephone Number(s), Hours of Operation, Backup Contact/Escalations, Email Address and Telephone Number(s).
12 | Customer Education | Deadline to issue first press release | Issue first press release | NANPA, FCC, Carriers | 2021-04-19 | 5-7 days prior to permissive effective date
13 | Customer Education | Carrier updates of directories | Carriers that publish directories need to add advisory to directories to alert customers of mandatory 10-digit dialing effective date | Carriers that publish directories | 2021-04-24 | No later than permissive 10-digit dialing effective date for customers
14 | Technical | Distribute carrier contact list | Distribute carrier contact list to carriers so they can contact each other as needed to troubleshoot any permissive 10-digit dialing issues | NANPA | 2021-04-24
15 | Technical | Carrier deadline to implement permissive 10-digit dialing | Carrier Deadline to have Permissive 10-Digit Dialing opened in their networks (Carriers can implement this any time up to this deadline, no need to wait until the night before to implement) | Carriers | 2021-04-24 | Same date as permissive 10-digit dialing effective date for customers |  | Carriers must notify NANPA via 988@somos.com when this milestone is completed. Include in email: Provider Name, OCN, State and NPA(s).
16 | Customer Education | Permissive 10-digit dialing effective date for customers | Permissive Dialing Effective Date - Date communicated to customers as the earliest date they can start dialing 10 digits | Carriers | 2021-04-24 | All dates above are calculated from this date
17 | Customer Education | Deadline to develop verbiage for second customer notice | Develop and supply template for second customer notification, a simple message about the upcoming mandatory 10-digit dialing "effective date" to remind customers to continue practicing dialing 10 digits and to complete reprogramming CPE by the mandatory 10-digit dialing effective date. Message must remind customers of what they need to do to prep for mandatory 10DD. Carriers can then tweak as needed depending on whether they want to send the same message to call customers, tweak for business customers, tweak for customers in particular NPAs, etc. | NANPA | 2021-05-27 | 150 days (5 months) prior to mandatory effective date | COMPLETE | Approved Mandatory Notice at 10/1/2020 meeting
18 | Customer Education | Deadline to develop and send second round of special letters | Develop and send second round of "special letters" to Directory Publishers, Coin Operated Payphone Providers, Alarm Associations, Highway Call Box Operators, and 911 State/County Coordinators & PSAPs reminding them of the mandatory dialing effective date, and what each of these types of groups need to do to prep for mandatory 10DD. Supply these templates to industry as well in case carriers want to use them to supplement their own customer notifications. | NANPA | 2021-06-26 | 120 days (4 months) prior to mandatory effective date
19 | Customer Education | Deadline to send second notice to PSAPs, PSALI and County Coordinators | Develop and send second/reminder notice to PSAPs, PSALI and County Coordinators of upcoming mandatory 10-digit dialing effective date and to update any speed calling or call forwarding numbers to 10 digits before that date. | 911 Providers | 2021-06-26 | 120 days (4 months) prior to mandatory effective date
20 | Customer Education | Deadline to develop verbiage for second press release | Develop and supply verbiage for a second Press Release to announce the mandatory 10-digit dialing effective date. Provide verbiage to industry, FCC and state commissions so they can issue press releases as well, as needed. | NANPA | 2021-07-26 | 90 days (3 months) prior to mandatory effective date
21 | Customer Education | Deadline to re-send second round of special letters as a reminder | Send second round of "special letters" again to Directory Publishers, Coin Operated Payphone Providers, Alarm Associations, Highway Call Box Operators, and 911 State/County Coordinators & PSAPs, reminding them of the mandatory dialing effective date, and what each of these types of groups need to do to prep for mandatory 10DD. Supply these templates to industry as well in case carriers want to use them to supplement their own customer notifications. | NANPA | 2021-09-09 | 45 days prior to mandatory effective date
22 | Customer Education | Deadline to refresh social media | Social media and website information updated regarding upcoming changes to dialing requirements due to Area Code Relief Refresh social media with information about the 82 NPAs that are transitioning to 10DD, noting the mandatory 10DD effective date so that customers can find relevant information. | Carriers (voluntary) | 2021-09-24 | 30 days prior to mandatory effective date
23 | Customer Education | Deadline to send second customer notice | Issue second customer notification. Carriers using bill messages may want to have these run multiple months rather than just one month to help ensure customers are aware of the upcoming dialing changes. | Carriers | 2021-09-24 | 30 days prior to mandatory effective date |  | Carriers must notify NANPA via 988@somos.com when this milestone is completed. Include in email: Provider Name, OCN(s), State(s) and NPA(s).
24 | Technical | Deadline for 10-digit signaling transition | Carriers should be signaling/sending 10 digits of the called to party for all calls terminating in all end offices and access tandems in the area code. | Carriers | 2021-09-24 | 30 days prior to mandatory effective date |  | Carriers must notify NANPA via 988@somos.com when this milestone is completed. Include in email: Provider Name, OCN(s), State(s) and NPA(s).
25 | Customer Education | Send reminder to PSAPs, PSALI and County Coordinators | Send reminder notice to PSAPs, PSALI and County Coordinators of upcoming mandatory 10-digit dialing effective date and to update any speed calling or call forwarding numbers to 10 digits | 911 Providers | 2021-09-24 | 30 days prior to mandatory effective date
26 | Technical | Update and re-distribute carrier contact list | Distribute carrier contact list to carriers so they can contact each other as needed to troubleshoot any mandatory 10-digit dialing issues | NANPA | 2021-10-17 | 7 days prior to mandatory effective date
27 | Customer Education | Deadline to issue second press release | Issue second Press Release | NANPA, FCC, Carriers | 2021-10-19 | 5-7 days prior to mandatory effective date
28 | Customer Education | Mandatory 10-digit dialing effective date for customers | Mandatory 10-Digit Dialing Effective Date - Communicated to Customers (This is the earliest date that carriers can begin removing 7DD and enforcing 10DD) | Carriers | 2021-10-24 | All dates between the permissive dialing effective date and this date are calculated from this date
29 | Technical | Deadline to update carrier systems that dial 7-digit numbers to dial 10 digits | Carriers to update all speed calling, call forwarding numbers and voicemail options in embedded databases to include the area code and reflect 10-digit dialing. Carriers to update any N11 calls translated to 7-digits to include the area code and reflect 10-digit dialing. | Carriers | TBD by each carrier | 30 days prior to carrier-specific mandatory enforcement date
30 | Technical | Deadline to have recorded announcements in place | Verify that switch can handle the recorded announcement and also that the announcement can be understood as that is what the customers will be hearing if they forget to dial 10 digits. | Carriers | TBD by each carrier | 30 days prior to carrier-specific mandatory enforcement date |  | Wireless and VoIP can implement a recorded announcement advising a customer that dials 7 to hang up and dial 10 (include the area code). Legacy wireline may not be able to implement such a recorded announcement though. In a legacy wireline switch, after mandatory 10-digit dialing is enforced and 988 is implemented as an abbreviated dialing code (likely at the same time), if a customer dials 988-XXXX, the call will route to the hotline. If the customer dials 988, the call will route to the hotline. If the customer dials NPA-988-XXXX, the call will complete to NPA-988-XXXX.
31 | Technical | Build E911 Network/Tandem Translations | Build E911 Network/Tandem Translations | 911 Providers | TBD by each carrier | 30 days prior to carrier-specific mandatory enforcement date |  | Ask 911 providers if this should be 30 days prior to mandatory effective date (communicated to customers) or 30 days prior to carrier-specific mandatory enforcement date
32 | Technical | Verify PSAP work | Get confirmation from PSAPs that all PSAP work has been completed | 911 Providers | TBD by each carrier | 30 days prior to carrier-specific mandatory enforcement date |  | Ask 911 providers if this should be 30 days prior to mandatory effective date (communicated to customers) or 30 days prior to carrier-specific mandatory enforcement date
33 | Technical | Carrier deadline to implement mandatory 10-digit dialing | Carrier Deadline to Enforce Mandatory 10-Digit Dialing (carriers have the interval between the mandatory 10DD effective date above and this deadline to remove 7DD and enforce 10DD on the schedule that works best for them) | Carriers | 2022-07-15 |  |  | Carriers must notify NANPA via 988@somos.com when this milestone is completed. Include in email: Provider Name, OCN(s), State and NPA(s).
Formulas:
Due Date = [Due Date, row below]